## 2 First Use/Playable (
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | What to do on this board | This board is here to be used for task management of tasks that need to be completed during the core milestone during PP2 Sprint planning - Understand an overall sprint goal (Rod should instruct you on that) - Select stories from the product backlog to achieve that goal - Move the selected userstories to this sprint board - Reviewed and edit test cases and task lists where needed based on the shifting vision of the game - Evaluate the difficulty/hours/complexity of the stories selected through planning poker - Distributing the workload among the team by assigning owners for all of the stories Sprint in action - Move userstories into the correct categories as you work to help everyone know what has and has not been completed - Log hours on tasks when they are worked on to both confirm effort placed on the task and the cost that was involved in adding that task to the game. - Peer check each other's work when it is completed to confirm integration and maintain a unified level of quality. |  |  |  |  | 3 | https://trello.com/c/3eP743QE
Important Notes | Code Freeze | Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. ● Before each milestone and sprint end, a final integration is needed. ○ Forces an integration at a safe time ○ Ensures there is time for testing and validation of the build ■ Confirm sprint goals ■ Peer check each other’s work |  |  |  |  | 1 | https://trello.com/c/ybLI7Qlw
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 2 | https://trello.com/c/VnUi6lUd

## Archived 2 First Use/Playable (
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL