## 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Info | Milestone Review | Not having a working build pushed to the milestone builds folder of the repo before the day of the milestone review is unacceptable. - All teams must have a zipped exe build in the “Milestone builds” folder - We aren’t working on user stories during class time on the day of the milestone - We aren’t integrating the builds during class time on the day of the milestone Previous sprint review - Finalize Trello board - - All user stories in final categories - - Hours spent on all tasks entered - Discus work problems if there were any - - If a user story estimate was off why was it off? Next sprint planning - Sprint goal must be understood - User stories moved from product backlog to sprint backlog that supports the sprint goal - Test cases and task lists reviewed for all sprint user stories Story allocation - Planning poker completed for all stories - User story owners assigned for all stories - Sprint plan reviewed and accepted by CD before the end of the lab It is Highly suggested that the team perform a code freeze no later then 4 hours before the milestone needs to be submitted. Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - Confirm sprint goals - - Peer check each other’s work |  | 2022-03-11 09:00 |  |  | 1 | https://trello.com/c/EyIVyU1q
Info | Team's agreed upon schedule | The team should agree upon a schedule when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 5 | https://trello.com/c/gY7wMx6q
Sprint Backlog (Alpha) | Completion scenario (winning the game, achieving achievements, high score) | Intent: - Create the win condition and all of the experience we intend to provide with it Notes on estimation: - Creating the trigger for a win screen is very fast and easy, presenting the actual win scenario of the game can vary in difficulty and time necessary based on how what will be done when the player wins |  |  |  |  | 2 | https://trello.com/c/fmMZytR5
Sprint Backlog (Alpha) | Loss condition and it is clear to the user when and how they lost | Intent: - Create loss condition and player feedback involved in it |  |  |  |  | 3 | https://trello.com/c/QwRN7g2L
Sprint Backlog (Alpha) | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. |  |  |  | TRC Requirement | 8 | https://trello.com/c/AkZdQltB
Incomplete | Cinemachine Implementation | We need a system for showing cutscenes to the player to convey the story. ******************* Time Estimate: 6h Story Points: 5 | 5 |  | TG |  | 23 | https://trello.com/c/LYpBgBWu
Incomplete | Story Spike | Story idea for the game to develop further in the month. ******************* Time Estimate: 1h Story Points: 1 | 1 |  | MC | Difficulty: Low,Priority: Medium | 18 | https://trello.com/c/qZGzs0dZ
Partially Complete | Revamp: Cooldown Clock for Abilities | We need to revamp the cooldown clock so that its visible to the player. Having this information in the UI at the bottom makes it so the player can't see this at all time. We need to fix that. ******************* Time Estimate: 2h Story Points: 2 | 2 |  | I | Difficulty: Low,Priority: High | 17 | https://trello.com/c/kbHLx0el
Partially Complete | Bud Creature Attack Ability | Bomb projectile that arches and explodes on touching the floor. (Old) Bud ability is an acid rain type projectiles that has AOE damage on enemies caught in it. A specialized creature attack specifically tailored to each creature. Players have a chance to pickup this attack for themselves upon enemy death. ******************* Time Estimate: 5h Story Points: 3 | 3 |  | I | Monster,Player,Ability System | 2 | https://trello.com/c/rMALTylv
Partially Complete | Shell Creature Attack Ability | Shield in front of the entity that blocks projectiles in that direction. A specialized creature attack specifically tailored to each creature. Players have a chance to pickup this attack for themselves upon enemy death. ******************* Time Estimate: 4h Story Points: 3 | 3 |  | I | Monster,Player,Ability System | 4 | https://trello.com/c/6b9o7sky
Partially Complete | Dragon Spark Attack Ability | Cone flamethrower, appears for a short moment before disappearing. A specialized creature attack specifically tailored to each creature. Players have a chance to pickup this attack for themselves upon enemy death. ******************* Time Estimate: 5h Story Points: 3 | 3 |  | I | Monster,Player,Ability System | 3 | https://trello.com/c/YrxH4hB8
Partially Complete | IPM Document | A plotting of the challenges the user faces while playing a game, against the time that that user has used the product. Notes on estimation: - This done as a team usually involves a couple hours of discussion as long as the mechanics of the game have been fully defined during pre production |  |  | MC |  | 7 | https://trello.com/c/ZiOIDUwC
Complete | Background music for the menus and levels | Intent: - Create ambiance and emotional tone for the game and levels. ******************* Time Estimate: 2h Story Points: 2 | 2 |  | DZ | TRC Requirement | 14 | https://trello.com/c/4W58RasJ
Complete | Revamp: Dragon AI Updates | We need an update AI system. The AI needs to function differently per enemy. This could be broken up into different stories.. Dragon AI Update - 3 points, 5 hours | 3 |  | DZ | Difficulty: Medium | 25 | https://trello.com/c/GpGJ5n5p
Complete | Revamp: Bud AI Update | We need an update AI system. The AI needs to function differently per enemy. This could be broken up into different stories.. Bud AI Update - 3 points, 5 hours | 3 |  | DZ |  | 26 | https://trello.com/c/qHZZH3Yr
Complete | Revamp: Shell AI Update | We need an update AI system. The AI needs to function differently per enemy. This could be broken up into different stories.. Shell AI Update - 3 points, 5 hours | 3 |  | DZ |  | 27 | https://trello.com/c/A4UHqdhg
Complete | Keyboard and mouse in-game | Intent: - Set up, test and use the default game controls for keyboard and mouse Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  |  | TRC Requirement | 12 | https://trello.com/c/ngc58Aoo
Complete | Ability to pause the game | Intent: - Allow the user to stop playing the game momentarily |  |  |  | TRC Requirement | 9 | https://trello.com/c/KqiciCqT
Complete | Navigate the main menu | Intent: - Create functionality for the main menu Note on estimation: - This is generally a very quick task since it is just the functionality of the menu (not final visuals) |  |  |  | TRC Requirement | 11 | https://trello.com/c/CSX4JysM
Complete | Revamp: Gameplay (damage indicators) | We need to revamp the core gameplay so that it's more balanced. We need to add damage indicators to the enemies so that the player gets visual feedback as to which attacks are effective and ineffective against the different enemy types. ******************* Time Estimate: 3h Story Points: 2 | 2 |  | I | Priority: Medium,Difficulty: Medium | 33 | https://trello.com/c/qe3wGRZg
Complete | Revamp: Gameplay (Number of shots) | We need to revamp the core gameplay so that it's more balanced. We need to tweak the amount of shots fired from an elemental ability so that the game allows the player to feel more powerful. ******************* Time Estimate: 0.5h Story Points: 0.5 | 0.5 |  | I | Priority: Medium,Difficulty: Low | 20 | https://trello.com/c/n9CwN6kr
Complete | Revamp item pickup system | We need a revamped pickup system that gives the player the choice to pickup an item. This will prevent them from automatically gaining an ability or item accidentally by walking into it. ******************* Time Estimate: 3h Story Points: 1 | 1 |  | I | Player,Player Interaction,Intractable Objects,Difficulty: Low | 11 | https://trello.com/c/IqqTl2GT
Complete | Revamp: Gameplay (Shooting Speed) | We need to revamp the core gameplay so that it's more balanced. We need to tweak the fire speed so that it doesn't feel as sluggish. Currently the fire speed is set to 2. ******************* Time Estimate: 0.5h Story Points: 0.5 | 0.5 |  | I | Difficulty: Low,Priority: Medium | 19 | https://trello.com/c/YV52GszQ
Complete | Frenzy Meter | We want to add a kill streak frenzy meter to the game. This will allow player to feel a rush of power and add a sense of accomplishment to the gameplay. ******************* Time Estimate: 3h Story Points: 5 | 5 |  | I | Priority: Medium,Difficulty: Low,Difficulty: Medium | 21 | https://trello.com/c/EpCvawEp
Complete | UI Updates because of Cooldown Changes | Since we've removed the cooldown clock above the players head, we need to tweak the UI to be more useful. ******************* Time Estimate: 2h Story Points: 2 | 2 |  | I | Priority: High,Difficulty: Medium | 35 | https://trello.com/c/uT9yXpvD
Complete | Loading screen when loading | Intent: - Provide a loading screen so the player is never unsure what the product is doing when they don't have control. https://docs.unity3d.com/ScriptReference/SceneManagement.SceneManager.LoadSceneAsync.html Note on estimation: - Creating the screen doesn't take very long. Complication is on getting the coroutine set up correctly, but following the unity docs or tutorials this rarely takes longer than a couple hours to do. ******************* Time Estimate: 1h Story Points: 1 | 1 |  | DZ | TRC Requirement | 4 | https://trello.com/c/XXlDTcsb
Complete | Keyboard and mouse for the game's menus | Intent: - Create control structure allowing keyboard and mouse to be used for all of the game's menus Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  | DZ | TRC Requirement | 10 | https://trello.com/c/XaGCwbxx
Complete | Audio feedback on the menus | Intent: - Inform the user that the input was entered ******************* Time Estimate: 1h Story Points: 1 | 1 |  | DZ | TRC Requirement | 13 | https://trello.com/c/bH1KVpLh
Complete | Change options in the game | Intent: - Allow the end users to change the settings for music and SFX volume Note on implementation: - The easiest way to implement this is through setting up mixer groups and then routing the various audio sources in the game through the right mixer group. An issue from mixer groups though is that they take volume in Db rather than a scaler 0 to 1 so it has to be converted. To roughly convert from a scaler value of 0-1 into logarithmic value for the unity mixer group is to use "Mathf.Log10(volume) * 20" Note on estimation: - Creating the menu doesn't take long. the difficulty and time involved on this one is in getting the mixer groups integrated in all of the audio sources in the game | 1 |  | DZ | TRC Requirement | 6 | https://trello.com/c/IDnW9vYl
Complete | Bose Enemy SO (Research Spike) | Research the enemies AI to determine if it's suitable for a boss enemy. There are two paths to this spike. 1. If the AI is suitable for reuse, we will setup and configure a new boss enemy and tweak the AI stats for a more challenging encounter. 2. If the AI is NOT suitable for reuse, our win condition will be destroying the spawners in each of the room before advancing. New User Stories will be created depending on the outcome. ******************* Time Estimate: 3h Story Points: 1 | 1 |  | DZ | Monster,Difficulty: Medium,Priority: High | 1 | https://trello.com/c/n1UliFQw
Complete | Remove Chest that have no interaction | Remove Chest that have no interaction in order to not confuse players. ******************* Time Estimate: 0.5h Story Points: 0.5 | 0.5 |  | MC | Medium Priority,Difficulty: Low | 15 | https://trello.com/c/dyY1lZKM
Complete | Additional Room - 7 | Additional Room #7 ******************* Time Estimate: 3h Story Points: 3 | 3 |  | MC | Difficulty: Medium,Priority: High | 28 | https://trello.com/c/Aac1lgSA
Complete | Additional Room - 6 | Additional Room #6 ******************* Time Estimate: 3h Story Points: 3 | 3 |  | MC | Priority: High,Difficulty: Medium | 14 | https://trello.com/c/TVG83ixw
Complete | Spike Trap | Simple spike traps are laid out in a pattern. They activate when stepped on and players must memorize the pattern to traverse ******************* Time Estimate: 2h Story Points: 2 | 2 |  | TG | Difficulty: Low,Priority: Medium | 22 | https://trello.com/c/qs3KO3jE
Complete | Pressure Plate System | Simple pressure plate system that uses triggers to activate. ******************* Time Estimate: 2h Story Points: 1 | 1 |  | TG | Priority: Medium,Difficulty: Low | 9 | https://trello.com/c/Ypkx3R1M
Complete | Flame thrower trap | Flame thrower trap activates when stepping into the trigger. Flames will sprout up towards the player causing damage. The flames will stop if the player moves off the plate. ******************* Time Estimate: 2h Story Points: 2 | 2 |  | TG | Priority: Medium,Difficulty: Low | 8 | https://trello.com/c/mqNDwDNH
Complete | Key Puzzle | Add puzzles to remove monotony from gameplay flow. The player will have to gather keys to open the door for this room. ******************* Time Estimate: 8h Story Points: 5 | 5 |  | TG | Priority: High,Difficulty: Hard | 16 | https://trello.com/c/by582WMc
Complete | Tutorial Text | We need some kind of way to communicate with the player how to play the game. We need some kind of pop-up text indicating the core elements of the game play. - Movement - Item Use (Chest, potion) - Attacks Basics - Attacks (Elemental System) - Objectives (how to clear a room) ******************* Time Estimate: 4h Story Points: 8 | 8 |  | MC | Priority: High,Difficulty: Hard | 13 | https://trello.com/c/SlCtzQQS
Complete | Sandbox / Tutorial Room | Sandbox rom/Debug room for the player. This room will consist of each element type placed on a pedestal. (Text describes each element) Players will be able to pickup each element and play with their powers. This is a small sandbox area. ******************* Time Estimate: 10h Story Points: 8 | 8 |  | MC | Design,Player Interaction,Priority: High,Intractable Objects,Difficulty: Low | 6 | https://trello.com/c/pamST0pA
Complete | Additional Room - 8 | Additional Room #8 ******************* Time Estimate: 3h Story Points: 3 | 3 |  | MC | Difficulty: Medium,Priority: High | 29 | https://trello.com/c/kOcGjrOY
Complete | Better "Intelligence scaling" | Our enemies can dodge attacks based off their intelligence score. As this score starts off big early, the enemies have a chance to dodge like masters as early as Room 1, making this game very difficult at the beginning. The intelligence score should be edited so that it starts as low as 0 and scales higher the more rooms you go through. |  |  | MC | Priority: Medium,Difficulty: Medium | 36 | https://trello.com/c/adIyEjJS

## Archived 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Added to Alpha Backlog | [archived] Spike Trap | Simple spike traps are laid out in a pattern. They activate on a timer and players must memorize the pattern to traverse |  |  | TG | Priority: Medium,Difficulty: Low | 5 | https://trello.com/c/gdJoxMgN
Added to Alpha Backlog | [archived] Rolling Boulder Trap |  |  |  | TG |  | 7 | https://trello.com/c/61H9jcaM
Added to Alpha Backlog | [archived] AI Update to think before attack (split story) | We need an update AI system. The AI needs to function differently per enemy. This could be broken up into different stories.. Dragon AI Update - 3 points, 5 hours Bud AI Update - 3 points, 5 hours Shell AI Update - 3 points, 5 hours |  |  | TG |  | 24 | https://trello.com/c/ZC5QrNBA
Added to Alpha Backlog | [archived] Tutorial Room | We need some kind of way to communicate with the player how to play the game. We need some kind of pop-up text indicating the core elements of the game play. - Movement - Item Use (Chest, potion) - Attacks Basics - Attacks (Elemental System) - Objectives (how to clear a room) ******************* Time Estimate: 10h Story Points: 8 | 8 |  | MC,TG | Difficulty: Hard,Priority: High | 34 | https://trello.com/c/W8UaqjLI
Added to Alpha Backlog | [archived] Additional Room #8 | Additional Room #5 ******************* Time Estimate: 3h Story Points: 3 | 3 |  | MC | Difficulty: Medium,Priority: High | 30 | https://trello.com/c/1tW9WCm0
Added to Alpha Backlog | [archived] Additional Room #9 | Additional Room #5 ******************* Time Estimate: 3h Story Points: 3 | 3 |  | MC | Difficulty: Medium,Priority: High | 31 | https://trello.com/c/11SNcVDa
Added to Alpha Backlog | [archived] Additional Room #10 | Additional Room #5 ******************* Time Estimate: 3h Story Points: 3 | 3 |  | MC | Difficulty: Medium,Priority: High | 32 | https://trello.com/c/qcsaLKcx
Added to Alpha Backlog | [archived] Showcase Level | A level that can be loaded with a debug menu button or debug key check that shows all of the created features in sequence. This would not be a level the users would ever see, just a space that proves the functionality works in an easily accessible way. This will be removed later for the final builds. **See Sandbox Ticket for more details** https://trello.com/c/pamST0pA/6-sandbox-room | ? |  | MC |  | 15 | https://trello.com/c/2tqC84a3
Added to Alpha Backlog | [archived] Revamp Item pickup system | [5 empty] | 10 | https://trello.com/c/6NLM0WG2
Added to Alpha Backlog | [archived] Tutorial Room | [5 empty] | 12 | https://trello.com/c/dyPp52vs