## 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Milestone Review | Not having a working build pushed to the milestone builds folder of the repo before the day of the milestone review is unacceptable. - All teams must have a zipped exe build in the “Milestone builds” folder - We aren’t working on user stories during class time on the day of the milestone - We aren’t integrating the builds during class time on the day of the milestone Previous sprint review - Finalize Trello board - - All user stories in final categories - - Hours spent on all tasks entered - Discus work problems if there were any - - If a user story estimate was off why was it off? Next sprint planning - Sprint goal must be understood - User stories moved from product backlog to sprint backlog that supports the sprint goal - Test cases and task lists reviewed for all sprint user stories Story allocation - Planning poker completed for all stories - User story owners assigned for all stories - Sprint plan reviewed and accepted by CD before the end of the lab It is Highly suggested that the team perform a code freeze no later then 4 hours before the milestone needs to be submitted. Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - Confirm sprint goals - - Peer check each other’s work |  | 2022-03-18 23:59 |  |  | 1 | https://trello.com/c/tRJmdbTJ
Important Notes | Team's agreed upon schedule | Monday - 5pm to 6pm EST Wednesday - 5pm to 6pm EST Friday - 5pm - 6pm EST Saturday - 12pm - 2pm EST (longer if needed) The team has agreed to meet on these days at this time, and will reflect our standup. |  |  | I,DZ,MC,TG |  | 16 | https://trello.com/c/0kIDty2q
Not Needed or Unknown | Play the game using an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Make the game playable on an android tablet If the game supports the tablet as its target platform. - If you have not already installed the packages necessary to export android build you can follow the directions how to do so here https://www.youtube.com/watch?v=4YNH9Y7NR3U |  |  |  | TRC Requirement,Target Platform | 14 | https://trello.com/c/xZajxxCz
Not Needed or Unknown | Controls function and be comfortable when playing the game on an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the player controls for a touch-based device if the game supports the tablet as its target platform. |  |  |  | TRC Requirement,Target Platform | 15 | https://trello.com/c/LbQZHKvz
Incomplete | Make sure rooms don't repeat | Rooms repeat sometimes, make sure that doesn't happen. ******************* Story Points: 1 |  |  | MC |  | 38 | https://trello.com/c/S8PXrva5
Incomplete | Dynamic Camera on Scene Load | We would like a dynamic camera to zoom out from the player when they enter a new level. It is VERY important to NOT override the main camera in the scenes via prefab. ******************* Story Points: 2 | 2 |  | TG | Low Priority | 3 | https://trello.com/c/0GvMNMUU
Incomplete | Review TRC Checklist | We need to ensure that our game follows the guidelines of the TRC. We need to go through the checklist and make sure our game is up to the standards set by the professor. | 1 |  | TG | Medium Priority | 35 | https://trello.com/c/MKqzAdk6
Incomplete | Pillars turn transparent when enemies are behind them |  |  |  | TG | Unplanned Work,Low Priority | 3 | https://trello.com/c/IAxcVk4n
Incomplete | Boss AI | We need the boss to be able to trigger AI states. ******************* Story Points: 5 | 5 |  |  | High Priority | 18 | https://trello.com/c/1mD83S4r
Incomplete | Boss Attack (AOE) | The boss should have some kind of AOE attack that the can activate. Maybe they can jump and on impact they create a shockwave that travels in a straight line. ******************* Story Points: 5 | 5 |  |  | Medium Priority | 19 | https://trello.com/c/TL4r3nH2
Incomplete | Boss Room - Atmosphere | The boss room needs to be decorated and having lighting that invokes a challenge. We want the visuals to represent the challenge ahead and the music to also reflect a boss fight. ******************* Story Points - 1 | 1 |  |  | High Priority | 26 | https://trello.com/c/RxrosCID
Incomplete | Boss Attack Lair Action (AOE) | There needs to be a boss lair action attack. Several runes will be laid out on the floor. At a random moment, the boss might choose to activate one of them. ******************* Story Points: 3 | 3 |  |  | Medium Priority | 21 | https://trello.com/c/xlOGEYOL
Incomplete | Boss Room - Base Room | We need a base room for the boss fights to take place. It doesn't need to be decorated, but the player should not be able to leave the room after they enter it, and they should not be able to enter the next room until the boss is defeated. ******************* Story Points: 2 | 2 |  |  | High Priority | 23 | https://trello.com/c/Mti1g6rJ
Partially Complete | Play the game in a browser using WebGL | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Get the game online and playable in a browser if the game supports the web as its target platform. - If you end up having issues with memory limits this blog post goes into the details on that a bit https://blogs.unity3d.com/2016/09/20/understanding-memory-in-unity-webgl/ |  |  | DZ | TRC Requirement,Target Platform | 7 | https://trello.com/c/vETeCsni
Partially Complete | Game Win Cutscene | We need a cutscene to wrap up the wizards quest, and something that teases a "whats next" for the wizard. ******************* Story Points: 3 | 3 |  | I | High Priority | 30 | https://trello.com/c/i1DhAjed
Complete | Installer for the game | Intent: - Create an installer for the product to make it easier to distribute. Note on estimation: - There should be little time needed to complete this task, An hour or two. Installers will be created using an installer creator application. ******************* Story Points - 1 | 1 |  | DZ | TRC Requirement | 10 | https://trello.com/c/gdkPiRSU
Complete | Controls to function and be comfortable when playing the game on the WebGL build | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the controls to be fully usable on web builds if the game supports the web player as its target platform. |  |  | DZ | TRC Requirement,Target Platform | 6 | https://trello.com/c/bOnuqd1Q
Complete | Play the game without needing to enable administrator mode | Intent: - Allow a larger user base by ensuring users do not need administrator access to the player the game after installation. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If the exe build did not ask for admin rights after saving was created on the last sprint it is unlikely that this will become an issue now. |  |  | DZ | TRC Requirement | 37 | https://trello.com/c/ZBlx7MTB
Complete | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. Story Points - 2 | 2 |  | I,MC,DB | TRC Requirement | 13 | https://trello.com/c/R1THU41T
Complete | Debug tools removal | Intent: - Finalizing the build to prepare for the quality assurance and submission process. Note on estimation: - Usually all this involves is commenting out the lines that trigger the debug functionality. This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. |  |  | DZ,DB,MC |  | 12 | https://trello.com/c/B6KGdo0R
Complete | Debugging, refactoring, and fixing scripts and game logic issues | Fixing issues with scripts, git commits, game logic, errors, etc. |  |  | DZ |  | 46 | https://trello.com/c/0f4S0BLT
Complete | Proper Title Display | We need to make this title of the game look nice and appear in the menu and on pause ******************* Story Points - 1 | 1 |  | DZ | Medium Priority | 13 | https://trello.com/c/bOGxD7Eh
Complete | Fix Menu Room - Don't show editor space through doors, holes in the floor or windows. | The main menu scene is showing the editor space through the empty doors holes in the floors, windows and any other open spaces as it rotates. We want this room to look like part of the world. We want to see this as a continuation of the room. Maybe have this looking into another room. Or a room with a torch, just not the emptiness of the void. ******************* Story Points: 2 | 2 |  | TG | Medium Priority | 24 | https://trello.com/c/yAROOpgF
Complete | Maintain a frame rate of at least 30 frames per second | Intent: - Maintain a smooth and clear game experience Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If however the game is already having issues with framerate at the point of estimating this card then the team should make their best judgement on the time to optimize where they think the slowdowns are located. |  |  |  | TRC Requirement | 4 | https://trello.com/c/AtoYxfSh
Complete | Game can be played on any monitor/TV set | Intent: - Allow the game to be played on any monitor/TV set. This is testing for screen bounds images sizes and aspect ratios Note on Implementation: - Other that HUD layout, having canvas scaler components handling how each screen scales to fit aspect ratios is the main things that needs to be done to support this. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. ******************* Story Points - 3 | 3 |  | DZ | TRC Requirement | 2 | https://trello.com/c/xwlanvXU
Complete | Player Dash | The player should be able to dash (move more quickly) when they want to, this will allow them to exit rooms quickly after they kill enemies. ******************* Story Points: 2 | 2 |  | DZ | Medium Priority | 42 | https://trello.com/c/enumbav9
Complete | Enemies need to spawn creature abilities on death | We need to have enemies on death drop the appropriate pickup: Lava -> Lava Tier 1 OR Dragon Breath Ice -> Ice Tier 1 OR Shell Sheild Nature -> Nature Tier 1 OR Acid Rain ******************* Story Points: 2 | 2 |  | DZ | High Priority | 15 | https://trello.com/c/GSLU6reM
Complete | AI Enemy Attack Rate Adjust | We need to balance how fast the enemies fire at the player, and make this adjustable in the inspector so we can do this per enemy per scene using inspector multipliers. ******************* Story Points - 1 | 1 |  | DZ | Low Priority | 12 | https://trello.com/c/KCGdKbCW
Complete | Monster Animation Improvement | The animations need to be better. ******************* Story Points: 5 | 5 |  | DZ | Low Priority | 16 | https://trello.com/c/ZSdZG89r
Complete | Experience the game without needing to have an additional player | Intent: - Ensure all players can experience a portion of the game without the need of an additional player on an online connection. Note on estimation: - This is mostly a verification at the end of the sprint and needs little if any time dedicated to it. If an entire new mode needs to be created to support this then there should be other cards defining that mode. |  |  |  | TRC Requirement | 5 | https://trello.com/c/GXfo1Ks9
Complete | Menu system final look and functionality | Intent: - Replace all placeholder assets with final ones - Ensure quality visuals throughout the product. |  |  | DZ |  | 8 | https://trello.com/c/XqKFZhJZ
Complete | Fix the traps in the levels | Traps are in place, but they are being triggered by the floor or other unknown force. We only want the traps to trigger on player enter. Not scene load. **Note:** Upon further investigation this is trigged because of the sphere collider on the enemies. Please update the triggers to only trigger when the player steps on them. ******************* Story Points: 1 | 1 |  | TG | Medium Priority | 14 | https://trello.com/c/nKGe08Nz
Complete | Randomize Chest Spawn Rate | We need a system for randomizing the chest so that they don't always appear in the same room or node each time. ******************* Story Points - 2 | 1 |  | MC | High Priority | 4 | https://trello.com/c/x5HyegRV
Complete | Swap out old monsters for new Pluggable AI ones | Daniel has created new AI that is attatched to a new set of monsters that we need to swap in for the old ones. ******************* Story Points: 1 |  |  | MC | High Priority | 45 | https://trello.com/c/WxRCVUg7
Complete | Custom Room for Ending Cutscene | We want to create a custom room to use in the cutscene at the beginning of the game. ******************* Story Points - 1 |  |  | MC | Low Priority | 44 | https://trello.com/c/f6D4pEo9
Complete | Scene for intro cutscene | Create a scene to use for the introductory cutscene. |  |  | MC | Medium Priority | 43 | https://trello.com/c/ae7QYK2U
Complete | Update Tutorial Room to explain Frenzy mechanic | In the tutorial room we need a way to convey what the frenzy mode is so that the player understands what it does. ******************* Story Points - 2 | 1 |  | MC | Low Priority | 6 | https://trello.com/c/K1eWdtOv
Complete | Game balancing - Enemy Spawn Rate | We need to adjust the enemy spawn rate for enemies so that the difficulty scales appropriately. ******************* | 1 |  | MC | High Priority | 8 | https://trello.com/c/MhFZ1tI6
Complete | Game balancing - Enemy Difficulty | We need to balance the difficulty of the enemies so that, in conjunction with the amount spawned, the player can win. ******************* Story Points - 1 | 1 |  | MC | High Priority | 9 | https://trello.com/c/2dhJWj8j
Complete | Game balancing - Item Spawn Rates | We need to balance the game so that the items spawn fairly. ******************* Story Points - 2 | 2 |  | MC | High Priority | 7 | https://trello.com/c/mtP0fjIw
Complete | Change Game Font - Stretch | We want to update the font of the game to match the theme. ******************* Story Points - 2 | 2 |  | TG,MC | Medium Priority | 34 | https://trello.com/c/dJNn6Tjj
Complete | Remove the distance limitations of the projectiles | Currently each ability has a "time to despawn" but this causes issues when you attack an enemy to far away only to not hit them. So we need to remove it. ******************* Story Points: 5 | 1 |  | I | Medium Priority | 41 | https://trello.com/c/73JYLv9q
Complete | Need Appropriate cooldown timer for creature abilities | Currently the word "Recharging" is not enough to signify to the player how long the cooldown is on their abilities. We need to make this some sort of visual cue. ******************* Story Points: 2 | 2 |  | I | Medium Priority | 40 | https://trello.com/c/EbBQjWKA
Complete | Identifiable icon | Intent: - Allow users to easily recognize the game from its icon image Note on estimation: - There should be very little time needed to complete this task. Adding an icon tot he game's exe using unity involves a drag and drop in the player settings. ******************* Story Points - 1 | 1 |  | I | TRC Requirement | 9 | https://trello.com/c/U5WXVAcq
Complete | Fix rotation and small issues with creature abilities | The creature abilities need some tweaking Story Points 2 | 2 |  | I | Medium Priority | 39 | https://trello.com/c/eWCG5UfM
Complete | Game Start Cutscene | When the game is started, we need some kind of cutscene to give an overview of the story and the purpose of the game to the player. ******************* Story Points: 5 | 5 |  | I | High Priority | 28 | https://trello.com/c/Buz9p3Yo
Complete | UI Room Counter | We want a UI counter to show which room the player is in to show the progression of the game. Room 1/8 ..... Room 4/8 ******************* Story Points: 1 | 1 |  | I | Medium Priority | 33 | https://trello.com/c/YJDOKLf8
Complete | Opening Game Cutscene | We need a system for showing the player the open scene either by cutscene or by scene. ******************* Story Points: 2 | 2 |  | I | Low Priority | 27 | https://trello.com/c/eyGsGNCr
Complete | Credits Cutscene | It would be nice to have a scrollable credit scene giving credit to each person who worked on the game and their roles. We also would want to credit the creators of the asset packs and music. ******************* Story Points: 2 | 2 |  | I | Low Priority | 32 | https://trello.com/c/ztvzynSk
Complete | Credits (everyone who contributed to creating the game to get credit for their work) | Intent: - Credit everyone who contributed to the product - For outsourced assets from web portals give enough information to be able to find the source of the asset (“Asset Name by AuthorName from website.com”) Note on estimation: - Time to complete this task is heavily dependent on if we have been maintaining a list of where we got our assets from or if we need to spend time to re-find the source of the assets. |  |  | I | TRC Requirement | 11 | https://trello.com/c/EnIvkVPh

## Archived 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | [archived] Cinemachine Implementation | We need a system for showing cutscenes to the player to convey the story. ******************* Time Estimate: 6h Story Points: 5 | 5 |  | I |  | 1 | https://trello.com/c/D9sEAqUn
Important Notes | [archived] Boss Attack - 2 | We need a system for showing cutscenes to the player to convey the story. ******************* Time Estimate: 6h Story Points: 5 | 1 |  | I |  | 20 | https://trello.com/c/imlGJAWL
Important Notes | [archived] Dynamic Camera on Scene Load |  |  |  | TG |  | 2 | https://trello.com/c/0LF7AWh7
Important Notes | [archived] Update Tutorial Room to explain Frenzy mechanic | [5 empty] | 5 | https://trello.com/c/qBKVE7od
Important Notes | [archived] UI Menu - Rotating Room (Custom) | [5 empty] | 10 | https://trello.com/c/3h7fPwvk
Important Notes | [archived] Boss Fight AI | [5 empty] | 17 | https://trello.com/c/HhDGsGNs
Important Notes | [archived] Boss Room - Decorating |  | 1 |  |  |  | 25 | https://trello.com/c/ZsCJNob6
Important Notes | [archived] Game End Cutscene | [5 empty] | 29 | https://trello.com/c/bFAMMdYl
Important Notes | [archived] |  | 1 |  |  |  | 22 | https://trello.com/c/KbVvh9Da
Sprint Backlog (Beta) | [archived] Pillars turn transparent when enemies are behind them | [5 empty] | 36 | https://trello.com/c/ypdHOkOM
Complete | [archived] Custom Room for Opening Cutscene | We want to create a custom room to use in the cutscene at the beginning of the game. ******************* Story Points - 1 | 1 |  | MC | Low Priority | 11 | https://trello.com/c/qdAhQzTX